## Sprint Retrospective
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action | Guidelines
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelin es
Example : All tasks were completed on time. Team communication was seamless. | Requirements changed mid-sprint. | Plan for a buffer to handle scope changes. | Set stricter deadlines for finalising requirements. | Example
AI question generation via Gemini integrated successfully. JWT authentication and role-based routing worked without issues. Student dashboard rendered correct data from MongoDB. | Face recognition login had low accuracy in poor lighting. Judge0 API rate limits caused code execution delays. Bulk CSV upload did not detect duplicate student emails. | Add a fallback to email/password when face auth fails. Cache identical Judge0 code submissions. Validate duplicate emails before DB insertion. | Implement OpenCV preprocessing to normalise lighting for face auth. Set up a local Judge0 instance for dev testing. Add server-side CSV validation in Sprint 2. | Sprint 1
Batch management and CSV bulk upload completed on schedule. Assessment assignment and real-time notifications working. Leaderboard and gamification points update correctly. | Gemini AI response time slow under concurrent requests. Results page had contrast issues in light theme. Coding platform timer did not persist after browser refresh. | Use Gemini streaming responses to reduce perceived latency. Audit all UI components for WCAG contrast compliance. Store timer state in localStorage to survive refreshes. | Enable Gemini streaming in the AI question generation service. Fix CSS variables for both themes on the Results page. Persist coding assessment timer via localStorage in Sprint 3. | Sprint 2